## Slide 1: PAAW / ASE Group Design Build and Test Status Update April 2, 2015

## Slide 3: Design, Build, and Test Status
mAEWing1
  Design v2.3 released
    Considered the Build-to configuration for the structure
    Wiring and system installation definition in-work (ECD 4/10)
  Build
    Wings nearing completion
      Actuators and linkages installed
      Final wiring and installation of accelerometer on-hold for parts (ECD 4/7)
    Centerbody held for parts
  Test
    Static and Dynamic wing tests complete for spars and wing forms
    Wing static and dynamic test (ECD 4/10)
    Freeplay test conducted,
mAEWing2
xAEWing3

## Slide 4: mAEWing1 Centerbody
Foam Components Received
  ~2” out of tolerance
  Supplier working remake, due next week

## Slide 5: mAEWing1 Wing Test Results
Left Wing
 | Mass (g) | EI (N-m^2) | GJ (N-m^2)
Target |  | 97.65 | 56.48
Predicted | Spar: 264 Wing Form: 365 Wing Form w/Fiber: 736 Complete Wing: 1354 | 97.43 | 59.13
Spar #6 | 312 | 105.95 (std = 5.40%) | 73.83 (std = 4.45%)
Wing Form | 693 | 143.89 (std = 7.13%) | 108.21 (std = 10.56%)
Wing Form w/ Fiberglass | 1126 |  | 
Complete Wing |  |  | 
Complete Wing w/Cuts |  |  | 
 | Mass (g) | EI (N-m^2) | GJ (N-m^2)
Target |  | 97.65 | 56.48
Predicted | Spar: 264 Wing Form: 365 Wing Form w/Fiber: 736 Complete Wing: 1354 | 97.43 | 59.13
Spar #5 | 308 | 108.81 (std = 4.98%) | 81.59 (std = 2.63%)
Wing Form | 663 | 127.96 (std = 2.54%) | 95.21 (std = 13.43%)
Wing Form w/ Fiberglass |  |  | 
Complete Wing |  |  | 
Complete Wing w/Cuts |  |  | 
Right Wing
Wings are stiffer and heavier than desired
  Excess adhesive used to bond the wing foam to the spar
    Left wing was very excessive, Right wing was slightly excessive
    Clear effect on weight, Unknown effect on stiffness

## Slide 6: mAEWing1 – Work Burndown
Completion slipped at least 1 week
  Held for parts; centerbody foam, plywood, hinges
Chart: 
| 10/12/14 | 10/26/14 | 11/9/14 | 11/23/14 | 12/7/14 | 12/21/14 | 1/4/15 | 1/18/15 | 2/1/15 | 2/15/15 | 3/1/15 | 3/15/15 | 3/29/15 | 4/12/15 | 4/26/15
Remaining Cumulative Work | 583.7833 | 539.7833 | 539.7833 | 539.7833 | 539.7833 | 539.7833 | 539.7833 | 457.7833 | 337.75 | 201.75 | 180.1 | 122.75 | 50.25 | 6.25 | 1.75
Remaining Cumulative Actual Work | 585.7833 | 541.7833 | 541.7833 | 541.7833 | 541.7833 | 541.7833 | 541.7833 | 459.7833 | 339.75 | 209.75 | 192.1 | 138.75 | 123.3833 | 123.3833 | 123.3833
Baseline Remaining Cumulative Work | 588.0333 | 544.0333 | 544.0333 | 544.0333 | 544.0333 | 544.0333 | 544.0333 | 462.0333 | 338 | 181 | 102.5 | 57.5 | 20.5 | 0 | 0